SPRINT PLAN — PHASE 1 MVP

PADA — 8 Weeks to Working Product

Solo founder + Claude agents. 4 sprints. One vertical slice per sprint. Ship a working end-to-end loop by Week 8.

| Field | Details |
| --- | --- |
| Team | Solo founder + Claude Code agents |
| Sprint Length | 2 weeks |
| Total Sprints | 4 (Phase 1 MVP) |
| Total Duration | 8 weeks — May to June 2026 |
| Total Points | 88 story points |
| Velocity Target | 20–24 pts/sprint (adjusted after Sprint 1) |
| Tracking | GitHub Issues + GitHub Projects Kanban |
| Definition of Done | All AC scenarios pass, Sentry wired, PostHog event firing, syncs to both devices |

Solo + Claude Agent Workflow: Each ticket becomes a GitHub Issue. Start a Claude Code session, point it at the issue, and let it implement → test → fix in a loop. You review, approve, and merge. Claude Code reads CLAUDE.md at session start for full project context — set that up before Sprint 1 begins.

# Point Scale & Conventions

| Points | Effort | Example | Who does it |
| --- | --- | --- | --- |
| 1 pt | < 1 hour | Add a field to a DB schema, write a Zod type | Claude agent, you review |
| 2 pts | Half day | Build a single UI screen with static data | Claude agent, you review |
| 3 pts | 1 day | Screen + API route + DB query end-to-end | Claude agent, you review + test |
| 5 pts | 2–3 days | Full feature: UI + API + sync + AC scenarios | Claude agent, you drive |
| 8 pts | Full sprint | Complex integration: OAuth + webhook + two-way sync | You + Claude, pair-style |

Agent tip: Break any 8-point ticket into two 3–5 point sub-tickets before handing to Claude. Agents work best on focused, well-scoped tasks with clear AC references. Anything that touches > 3 files in > 2 packages should be split.

| Sprint 1 — Foundation & Core Loop | Week 1–2 ¦ May 5–16 | 22 pts |
| --- | --- | --- |

Goal: Working end-to-end loop — type a task on iPhone, it saves locally, syncs to the server, appears on Mac. No AI yet. No auth polish. Just the core data path working.

| Ticket | Title | Area | AC Refs | Pts |
| --- | --- | --- | --- | --- |
| S1-01 | Turborepo monorepo scaffold — apps/web, apps/mobile, apps/mac-shell, packages/types, extensions/ | Infra | — | 2pt |
| S1-02 | packages/types — Task, User, Attachment TypeScript interfaces with Zod schemas | DB | — | 1pt |
| S1-03 | Neon Postgres setup + Drizzle schema (tasks, users, integrations, pending_sync tables) | DB | — | 2pt |
| S1-04 | Next.js 15 App Router skeleton — health check route, env config, Sentry wired | Backend | — | 2pt |
| S1-05 | Auth.js v5 — Apple Sign In + session middleware on all /api/* routes | Auth | AC-032 | 3pt |
| S1-06 | POST /api/v1/tasks — create task, validate with Zod, write to Neon Postgres | Backend | AC-001 | 2pt |
| S1-07 | GET /api/v1/tasks — fetch task list for authed user, paginated | Backend | AC-001 | 1pt |
| S1-08 | Expo app scaffold — Expo Router 4, NativeWind 4, Zustand store, TanStack Query | Mobile | — | 2pt |
| S1-09 | expo-sqlite setup — migration runner, Task repository (insert, list, update, delete) | Mobile | AC-003 | 2pt |
| S1-10 | Capture screen — text input, save button, writes to local SQLite optimistically | Mobile | AC-001 | 2pt |
| S1-11 | Inbox screen — list from SQLite, pull-to-refresh, tap to detail | Mobile | AC-001 | 1pt |
| S1-12 | Sync: on save, POST to /api/v1/tasks; on launch, GET and reconcile with local DB | Mobile | AC-014 | 2pt |
| S1-13 | PostHog wired — task_created, app_opened, sync_success events (no PII) | Infra | — | 1pt |
| S1-14 | Sprint 1 QA pass — run AC-001, AC-003, AC-032 manually on device | Mobile | AC-001,003 | 1pt |

Sprint 1 exit criteria: A task typed on iPhone appears in Neon Postgres within 3 seconds. The inbox lists tasks fetched from the server on launch. Auth flow completes with Apple Sign In. Sentry and PostHog receiving events.

| Sprint 2 — AI Layer + Mac Menu Bar | Week 3–4 ¦ May 19–30 | 24 pts |
| --- | --- | --- |

Goal: Claude parses tasks from natural language. Mac menu bar shows tasks and quick-add works. CloudKit syncs iPhone to Mac in real time.

| Ticket | Title | Area | AC Refs | Pts |
| --- | --- | --- | --- | --- |
| S2-01 | Vercel AI SDK setup — @ai-sdk/anthropic, generateObject, rate limit middleware in Vercel KV | AI | — | 2pt |
| S2-02 | POST /api/v1/ai/parse — task parsing with generateObject + Zod schema, confidence score | AI | AC-020 | 3pt |
| S2-03 | On-device NLP pre-pass — date/priority extraction before AI call (reduces latency + tokens) | AI | AC-002 | 2pt |
| S2-04 | Capture screen — wire AI parse: raw input → /api/v1/ai/parse → preview chip → confirm | Mobile | AC-002,020 | 3pt |
| S2-05 | Voice capture — @react-native-voice/voice, streaming transcription, silence detection | Mobile | AC-004,005 | 3pt |
| S2-06 | CloudKit Expo Module (Swift, ~200 lines) — write task to CloudKit Private Database zone | Sync | AC-014 | 5pt |
| S2-07 | CloudKit delta sync — fetch changes on foreground, CKSyncEngine change token management | Sync | AC-014,015 | 3pt |
| S2-08 | Mac Swift shell scaffold — Xcode project, NSStatusItem, signed DMG build via GitHub Actions | Mac | — | 2pt |
| S2-09 | Mac popover — NSPopover + WKWebView loading Next.js /popover route | Mac | AC-016 | 2pt |
| S2-10 | Next.js /popover page — minimal quick-add UI, POSTs to /api/v1/tasks, closes on save | Backend | AC-016 | 2pt |
| S2-11 | Global keyboard shortcut — NSEvent monitor, Cmd+Shift+P opens/closes popover | Mac | AC-016 | 1pt |
| S2-12 | Mac badge count — NSStatusItem badge polls /api/v1/tasks/count every 30s | Mac | AC-014 | 1pt |
| S2-13 | Sprint 2 QA — AC-002, AC-004, AC-014, AC-015, AC-016 on device + Mac | Mobile | multi | 2pt |

Sprint 2 exit criteria: Natural language input parsed by Claude with due date + priority extracted. Task created on iPhone appears in Mac menu bar badge within 2 seconds via CloudKit. Popover quick-add creates tasks visible on iPhone. AI parse time < 2s.

| Sprint 3 — Developer Tools + Email | Week 5–6 ¦ Jun 2–13 | 22 pts |
| --- | --- | --- |

Goal: VS Code extension captures coding tasks. GitHub issues sync as tasks. Gmail connected with AI action extraction. Daily briefing fires.

| Ticket | Title | Area | AC Refs | Pts |
| --- | --- | --- | --- | --- |
| S3-01 | VS Code/Cursor/Windsurf extension — scaffold, auth token, Cmd+Shift+T command | DevTools | AC-022 | 3pt |
| S3-02 | Extension core — POST to /api/v1/tasks with file, line, repo, branch context | DevTools | AC-022 | 2pt |
| S3-03 | Extension marketplace publish — VS Code Marketplace, open-vsix for Cursor/Windsurf | DevTools | AC-022 | 1pt |
| S3-04 | Neovim Lua plugin — :PadaAdd command, HTTP to /api/v1/tasks, repo context via git | DevTools | AC-024 | 2pt |
| S3-05 | GitHub OAuth + webhook setup — /api/v1/oauth/github, /api/v1/webhook/ingest | DevTools | AC-025 | 3pt |
| S3-06 | GitHub issue → PADA task — webhook handler maps issue.assigned event to task | DevTools | AC-025 | 2pt |
| S3-07 | CI/CD failure alerts — GitHub Actions failure webhook → P1 task with log excerpt | DevTools | AC-028 | 2pt |
| S3-08 | Gmail OAuth flow — Auth.js Gmail provider, scopes: read + send + labels, PKCE | Backend | AC-029 | 3pt |
| S3-09 | Email thread view — fetch thread via Gmail API, render in task detail | Mobile | AC-030 | 2pt |
| S3-10 | AI action extraction — POST /api/v1/ai/extract-actions, generateObject returns task list | AI | AC-030 | 2pt |
| S3-11 | Daily briefing — Vercel Cron at 7am, generateText briefing, push via APNs | AI | AC-018 | 2pt |
| S3-12 | Task routing to Apple Reminders — NSAppleScript from Mac shell, routed_to field update | Mac | AC-017 | 2pt |
| S3-13 | Sprint 3 QA — AC-017, AC-018, AC-022, AC-024, AC-025, AC-028, AC-029, AC-030 | DevTools | multi | 2pt |

Sprint 3 exit criteria: Highlight a TODO in VS Code → task appears in PADA inbox. GitHub issue assigned → task created automatically. Gmail connected, email thread opens in app, action items extracted by AI. Daily briefing notification fires at 7am.

| Sprint 4 — Polish, Share Extension & Launch Prep | Week 7–8 ¦ Jun 16–27 | 20 pts |
| --- | --- | --- |

Goal: Share Extension working. AI reply drafting working. Offline mode solid. All 37 AC scenarios passing. TestFlight + DMG ready for beta users.

| Ticket | Title | Area | AC Refs | Pts |
| --- | --- | --- | --- | --- |
| S4-01 | iOS Share Extension (Expo Module, Swift ~200 lines) — capture from Safari, Mail, any app | Mobile | AC-008 | 5pt |
| S4-02 | Photo capture — Vision Camera + mlkit-ocr, editable preview, image attached to task | Mobile | AC-006,007 | 3pt |
| S4-03 | AI reply drafting — streamText, bullet points → full email draft, streaming to mobile | AI | AC-031 | 3pt |
| S4-04 | Task detail — sub-tasks, attachments, delegation flow UI, priority/category edit | Mobile | AC-010,011 | 3pt |
| S4-05 | Offline mode — pending_sync queue, retry with backoff, offline badge on tasks | Mobile | AC-003 | 2pt |
| S4-06 | Conflict resolution UI — side-by-side diff when CloudKit conflict detected | Sync | AC-015 | 2pt |
| S4-07 | Linear OAuth + two-way sync — /api/v1/oauth/linear, webhook, status mirroring | DevTools | AC-026 | 3pt |
| S4-08 | Onboarding flow — Apple Sign In, notifications permission, optional GitHub/Gmail connect | Mobile | AC-032,033 | 2pt |
| S4-09 | Notifications — overdue alert at 9am, reminder_date fires, deep link into task | Mobile | AC-012,018 | 2pt |
| S4-10 | Performance pass — cold start < 1.5s, sync latency measured, AI parse < 2s logged | Infra | AC-034,035 | 2pt |
| S4-11 | Security audit — Keychain storage verified, no PII in Sentry/PostHog, TLS confirmed | Infra | AC-036 | 1pt |
| S4-12 | Full AC regression — all 37 scenarios across AC-001 to AC-037 | Mobile | all | 2pt |
| S4-13 | TestFlight build via EAS Submit + notarised Mac DMG on GitHub Release | Infra | — | 1pt |
| S4-14 | CLAUDE.md update — reflect actual file structure, any conventions that emerged | Infra | — | 1pt |

Sprint 4 exit criteria: All 37 AC scenarios pass. Share Extension captures from Safari. Reply drafting streams to the app. TestFlight build live for beta testers. Signed DMG on GitHub Releases. Performance targets hit. Phase 1 MVP shipped.

# Phase 1 Summary

| Sprint | Focus | Points | End Date |
| --- | --- | --- | --- |
| Sprint 1 | Foundation — monorepo, auth, DB, basic capture + sync | 22 pts | May 16, 2026 |
| Sprint 2 | AI parsing, voice, CloudKit sync, Mac menu bar | 24 pts | May 30, 2026 |
| Sprint 3 | IDE extensions, GitHub, Gmail, daily briefing | 22 pts | Jun 13, 2026 |
| Sprint 4 | Share Extension, polish, offline, full AC pass, ship | 20 pts | Jun 27, 2026 |
| Total | Phase 1 MVP — all 37 AC scenarios green | 88 pts | Jun 27, 2026 |

# Working with Claude Agents — Ticket Workflow

This is how to run each ticket efficiently as a solo founder with Claude Code as your engineering team.

| Step | What to do |
| --- | --- |
| 1. Open ticket | Open the GitHub Issue. Read the title, AC refs, and points. |
| 2. Start Claude Code | cd into the monorepo root. Claude Code reads CLAUDE.md automatically. |
| 3. Give the ticket | Paste: 'Implement S1-06: POST /api/v1/tasks. See AC-001 in the AC doc. Use Drizzle + Neon. Validate with Zod from packages/types.' |
| 4. Let it run | Claude Code will read relevant files, write the implementation, run tests, and fix errors in a loop. Don't interrupt unless it gets stuck. |
| 5. Review the diff | Read every file changed. Check it matches the AC scenario. Run the scenario manually on device. |
| 6. Merge + close | Squash merge to main. Close the GitHub Issue. Vercel auto-deploys. EAS Update ships JS to TestFlight. |
| 7. Next ticket | Start the next one. Keep Claude Code's context window clean — start a new session per ticket. |

One session per ticket: Don't chain multiple tickets in one Claude Code session. Context window fills up and quality drops. Start fresh per ticket — CLAUDE.md gives it all the project context it needs.

# Sprint Risks & Mitigations

| Risk | Sprint | Mitigation |
| --- | --- | --- |
| CloudKit Expo Module harder than expected | S2 | Spike first day of Sprint 2. If > 2 days, use Neon Postgres sync instead and add CloudKit in Phase 2. |
| Apple Sign In review delay | S1 | Start Apple Sign In developer setup before Sprint 1 begins — needs Apple Developer account config. |
| VS Code extension signing/publish | S3 | Read marketplace publish docs in Sprint 2. Marketplace approval takes 1–2 days. |
| Gmail OAuth Google review | S3 | Submit for Google OAuth verification early — review can take 1–2 weeks. Use test accounts meanwhile. |
| AI streaming in React Native | S2 | Spike streaming approach Day 1 of Sprint 2. Fall back to polling if SSE/ReadableStream issues. |
| Sprint velocity miscalibrated | S1 | After Sprint 1 actuals, recalibrate. 22 pts may be too many or too few. Adjust Sprint 2 accordingly. |

Before Sprint 1 starts: 1) Resolve 5 open questions from PRD Section 13. 2) Set up CLAUDE.md (see companion file). 3) Apple Developer account active. 4) Vercel, Neon, EAS accounts created. 5) GitHub repo created with branch protection on main.